## MMS
PEP-II MMS and D&D Plan Cost Estimations |  |  |  | J. Seeman |  | 2009-03-03
PEP-II Minimum Maintenance State Effort
Year | Role | Task | Group | FTE-yr | M&S | Cost for labor | Total
[5 empty] | (k$) | (k$) | Cost
(k$)
FY2009:
PEP-II accelerator work:
FY09 | Area Manager | Coordinate MMS | ASD | 0.5 | 15 | 100 | 115
FY09 | Area Physicist | Coordinate MMS | ASD | 0.25 | 5 | 67 | 72
FY09 | Documentation | Document PEP-II components | ASD | 0.25 | 5 | 50 | 55
FY09 | Documentation Supervisor | Document PEP-II components | ASD | 0.15 | 5 | 30 | 35
FY09 | Mechanical engineer | Secure mechanical hazards | ASD | 0.1 | 5 | 20 | 25
FY09 | Mechanical technician | Drain and dry magnet coils | MFD | 1 | 50 | 180 | 230
FY09 | Mechanical supervisor | Drain and dry magnet coils | MFD | 0.25 | 10 | 50 | 60
FY09 | Mechanical technician | Drain and dry H2O for vacuum chambers | MFD | 1 | 65 | 180 | 245
FY09 | Mechanical supervisor | Drain and dry H2O for vacuum chambers | MFD | 0.25 | 10 | 33 | 43
FY09 | RF technician | Secure the RF system | Klys | 0.25 | 60 | 50 | 110
Tunnel facility maintenance and security:
FY09 | Mechanical technician | Maintain tunnel fire-protection systems | CEF | 0.2 | 10 | 36 | 46
FY09 | Mechanical technician | Maintain tunnel water drain systems | CEF | 0.2 | 60 | 36 | 96
FY09 | Mechanical supervisor | Maintain tunnel mechanical systems | CEF | 0.2 | 10 | 36 | 46
FY09 | Electrical technician | Maintain tunnel lighting systems | CEF | 0.1 | 20 | 18 | 38
FY09 | Electrical supervisor | Maintain tunnel lighting systems | CEF | 0.1 | 10 | 18 | 28
FY09 | Security Officer | Maintain tunnel safety walkthrus | ASD | 0.1 | 0 | 18 | 18
FY09 | ESH activities | Safety and supervision | ESH | 0.1 | 20 | 18 | 38
FY09 | Crane maintenance/checks | Secure and certify cranes in IR halls | CSE | 0.1 | 13 | 18 | 31
FY09 | Controls maintenance | Keep control system reading safety systems | CSE | 0.1 | 15 | 18 | 33
FY09 | Controls maintenance sprv | Keep control system reading safety systems | CSE | 0.1 | 5 | 20 | 25
FY09 | Power | Lights, water pumps, sumps, safety systems |  |  | 514 | 10 | 524
FY09 | Totals |  |  | 5.3 | 907 | 1006 | 1913
FY10:
PEP-II accelerator work:
FY10 | Area Manager | Coordinate MMS | ASD | 0.5 | 15 | 100 | 115
FY10 | Area Physicist | Coordinate MMS | ASD | 0.25 | 5 | 67 | 72
FY10 | Documentation | Document PEP-II components | ASD | 0.1 | 5 | 20 | 25
FY10 | Mechanical engineer | Secure mechanical hazards | ASD | 0.1 | 5 | 20 | 25
FY10 | Mechanical technician | Drain and dry magnet coils | MFD | 0.25 | 50 | 45 | 95
FY10 | Mechanical supervisor | Drain and dry magnet coils | MFD | 0.1 | 10 | 20 | 30
FY10 | Mechanical technician | Drain and dry H2O for vacuum chambers | MFD | 0.25 | 65 | 45 | 110
FY10 | Mechanical supervisor | Drain and dry H2O for vacuum chambers | MFD | 0.25 | 10 | 33 | 43
FY10 | RF technician | Secure the RF system | Klys | 0.25 | 60 | 50 | 110
Tunnel facility maintenance and security:
FY10 | Mechanical technician | Maintain tunnel fire-protection systems | CEF | 0.2 | 10 | 36 | 46
FY10 | Mechanical technician | Maintain tunnel water drain systems | CEF | 0.2 | 30 | 36 | 66
FY10 | Mechanical supervisor | Maintain tunnel mechanical systems | CEF | 0.2 | 10 | 36 | 46
FY10 | Electrical technician | Maintain tunnel lighting systems | CEF | 0.1 | 20 | 18 | 38
FY10 | Electrical supervisor | Maintain tunnel lighting systems | CEF | 0.1 | 10 | 18 | 28
FY10 | Security Officer | Maintain tunnel safety walkthrus | ASD | 0.1 | 0 | 18 | 18
FY10 | ESH activities | Safety and supervision | ESH | 0.1 | 20 | 18 | 38
FY10 | Crane maintenance/checks | Secure and certify cranes in IR halls | CSE | 0.1 | 13 | 18 | 31
FY10 | Controls maintenance | Keep control system reading safety systems | CSE | 0.1 | 15 | 18 | 33
FY10 | Controls maintenance sprv | Keep control system reading safety systems | CSE | 0.1 | 5 | 20 | 25
FY10 | Power | Lights, water pumps, sumps, safety systems |  |  | 366 | 10 | 376
FY10 | Totals |  |  | 3.35 | 724 | 646 | 1370
FY11:
PEP-II accelerator work:
FY11 | Area Manager | Coordinate MMS planning | ASD | 0.5 | 39 | 100 | 139
FY11 | Area Physicist | Coordinate MMS | ASD | 0.25 | 5 | 67 | 72
FY11 | Documentation | Document PEP-II components | ASD | 0.1 | 5 | 20 | 25
FY11 | Mechanical engineer | Secure mechanical hazards | ASD | 0.1 | 5 | 20 | 25
FY11 | RF technician | Secure the RF system | Klys | 0.25 | 60 | 50 | 110
Tunnel facility maintenance and security:
FY11 | Mechanical technician | Maintain tunnel fire-protection systems | CEF | 0.2 | 10 | 36 | 46
FY11 | Mechanical technician | Maintain tunnel water drain systems | CEF | 0.2 | 30 | 36 | 66
FY11 | Mechanical supervisor | Maintain tunnel mechanical systems | CEF | 0.2 | 10 | 36 | 46
FY11 | Electrical technician | Maintain tunnel lighting systems | CEF | 0.1 | 20 | 18 | 38
FY11 | Electrical supervisor | Maintain tunnel lighting systems | CEF | 0.1 | 10 | 18 | 28
FY11 | Security Officer | Maintain tunnel safety walkthrus | ASD | 0.1 | 0 | 18 | 18
FY11 | ESH activities | Safety and supervision | ESH | 0.1 | 20 | 18 | 38
FY11 | Crane maintenance/checks | Secure and certify cranes in IR halls | CSE | 0.1 | 13 | 18 | 31
FY11 | Controls maintenance | Keep control system reading safety systems | CSE | 0.1 | 15 | 18 | 33
FY11 | Controls maintenance sprv | Keep control system reading safety systems | CSE | 0.1 | 5 | 20 | 25
FY11 | Power | Lights, water pumps, sumps, safety systems |  |  | 280 | 10 | 290
FY11 | Totals |  |  | 2.5 | 527 | 503 | 1030
PEP-II D&D Effort
Year | Role | Task | Group | FTE-yr | M&S | Cost for labor | Total
[5 empty] | (k$) | (k$) | Cost
FY2009: | [6 empty] | (k$)
PEP-II D&D work:
FY09 | Area Physicist | Coordinate D&D planning | ASD | 0.25 | 5 | 67 | 72
FY09 | D&D documentation | Develop document for PEP-II D&D | ETS | 0.25 | 25 | 50 | 75
FY09 | Mechanical engineer | Explore mechanical removal plans | ASD | 0.25 | 10 | 50 | 60
FY09 | RF engineer | Explore RF removal plans | Klys | 0.25 | 60 | 50 | 110
FY09 | ESH | Explore release an suspension materials | ESH | 0.4 | 60 | 79 | 139
FY09 | ESH | Explore rad waste chacterization | ESH | 0.25 | 60 | 50 | 110
FY09 | Totals |  |  | 1.65 | 220 | 346 | 566
FY2010:
PEP-II D&D work:
FY10 | Area Physicist | Coordinate D&D planning | ASD | 0.25 | 5 | 67 | 72
FY10 | D&D documentation | Develop document for PEP-II D&D | ETS | 0.5 | 25 | 100 | 125
FY10 | Mechanical engineer | Explore mechanical removal plans | ASD | 0.5 | 10 | 100 | 110
FY10 | RF engineer | Explore RF removal plans | Klys | 0.15 | 10 | 31 | 41
FY10 | Mechanical engineer | Explore shipping protocols and containers | ASD | 0.5 | 10 | 100 | 110
FY10 | ESH | Explore release an suspension materials | ESH | 1 | 50 | 200 | 250
FY10 | ESH | Develop export and shipping documentation | ESH | 1 | 25 | 200 | 225
FY10 | ESH | Explore rad waste chacterization | ESH | 1 | 50 | 200 | 250
FY2010 | Totals |  |  | 4.9 | 185 | 998 | 1183
FY2011:
PEP-II D&D work:
FY11 | Area Physicist | Coordinate D&D planning | ASD | 0.25 | 5 | 67 | 72
FY11 | D&D documentation | Develop document for PEP-II D&D | ETS | 0.5 | 25 | 100 | 125
FY11 | Mechanical engineer | Explore mechanical removal plans | ASD | 0.5 | 10 | 100 | 110
FY11 | RF engineer | Explore RF removal plans | Klys | 0.15 | 10 | 31 | 41
FY11 | Mechanical engineer | Explore shipping protocols and containers | ASD | 0.3 | 10 | 67 | 77
FY11 | ESH | Explore release an suspension materials | ESH | 1 | 50 | 200 | 250
FY11 | ESH | Develop zoning calculation documentation | ESH | 1 | 25 | 200 | 225
FY11 | ESH | Explore rad waste chacterization | ESH | 1 | 50 | 200 | 250
FY11 | Contractor | Cost removal plan |  | 3 | 50 | 400 | 450
FY2011 | Totals |  |  | 7.7 | 235 | 1365 | 1600
FY2012:
PEP-II D&D work:
FY11 | Area Physicist | Coordinate D&D planning | ASD | 0.25 | 5 | 67 | 72
FY11 | D&D documentation | Develop document for PEP-II D&D | ETS | 0.5 | 25 | 100 | 125
FY11 | Mechanical engineer | Explore mechanical removal plans | ASD | 0.5 | 10 | 100 | 110
FY11 | RF engineer | Explore RF removal plans | Klys | 0.15 | 10 | 31 | 41
FY11 | Mechanical engineer | Explore shipping protocols and containers | ASD | 0.3 | 10 | 67 | 77
FY11 | ESH | Explore release an suspension materials | ESH | 1 | 50 | 200 | 250
FY11 | ESH | Develop zoning calculation documentation | ESH | 1 | 25 | 200 | 225
FY11 | ESH | Explore rad waste chacterization | ESH | 1 | 50 | 200 | 250
FY11 | Contractor | Cost rad waste burial plan |  | 2 | 50 | 350 | 400
FY11 | Contractor | Cost removal plan |  | 3 | 50 | 400 | 450
FY2012 | Totals |  |  | 9.7 | 285 | 1715 | 2000

## DnD
PEP-II DND Planning Budget |  | J. Seeman |  |  |  | 2008-02-16
Year | Role | Task | Group | FTE-yr | M&S | Cost for labor | Total | HEP Job Category
[5 empty] | (k$) | (FTE=130k$) | Cost
(k$)
PEP-II DND Planning Team:
FY08 | DND Manager | Coordinate DND | ASD | 0.5 | 5 | 65 | 70
FY08 | Area Physicist | Coordinate DND | ASD | 0.5 | 5 | 65 | 70
FY08 | Facilities Engineer | Document PEP-II components | CEF | 0.5 | 5 | 65 | 70
FY08 | ESH Engineer | Document PEP-II components | ESH | 0.5 | 5 | 65 | 70
FY08 | Electrical Engineer | Secure electrical hazards | CEF | 0.5 | 5 | 65 | 70
FY08 | Totals |  |  | 2.5 | 25 | 325 | 350
FY09 | DND Manager | Coordinate DND | ASD | 1 | 25 | 130 | 155
FY09 | Area Physicist | Coordinate DND | ASD | 0.5 | 5 | 65 | 70
FY09 | Facilities Engineer | Document PEP-II components | CEF | 2 | 25 | 260 | 285
FY09 | ESH Engineer | Document PEP-II components | ESH | 1 | 25 | 130 | 155
FY09 | Electrical Engineer | Secure electrical hazards | CEF | 1 | 25 | 130 | 155
FY09 | Totals |  |  | 5.5 | 105 | 715 | 820
FY10 | DND Manager | Coordinate DND | ASD | 1 | 50 | 130 | 180
FY10 | Area Physicist | Coordinate DND | ASD | 0.5 | 5 | 65 | 70
FY10 | Facilities Engineer | Document PEP-II components | CEF | 2 | 50 | 260 | 310
FY10 | ESH Engineer | Document PEP-II components | ESH | 2 | 50 | 260 | 310
FY10 | Electrical Engineer | Secure electrical hazards | CEF | 1 | 50 | 130 | 180
FY10 | Totals |  |  | 6.5 | 205 | 845 | 1050